# MODULE 1: MANAGEMENT STUDIO

Họ tên : Nguyễn Thị Nga

MSSV : 21130791

## Exercise 1. Creating a link

Task:

- Default: start, duration, predescessor

- Summary: gom nhóm các task

- Task lặp đi lặp lại: Chu kỳ,

- Milstone: cột mốc

Creating the following tasks

| ID | TASK NAME | PREDESCESSOR | DURATION |
| --- | --- | --- | --- |
| 1 | Research destinations | - | 2 days |
| 2 | Book flights | 1 | 1 day |
| 3 | Prepare and pack | 2 | 5 days |
| 4 | Fly out | 3 | 1 day |
| 5 | Relax in the sun | 4 | 7 days |
| 6 | Fly home | 5 | 1 day |
| 7 | Peel | 6 | 7 days |

- Display the Project Information

- View Project Timeline, Gant Chart, Network Diagram and capture the result them.

## Exercise 2. Setting duration

Creating the following tasks \

| ID | TASK NAME | PREDESCESSOR | DURATION |
| --- | --- | --- | --- |
| 1 | Quarry stone | - | 2 days |
| 2 | Transport stone | 1 | 1 days |
| 3 | Prepare stone | 2 | 5 days |
| 4 | Fill foundations | 1,3 | 1 day |
| 5 | Level ground | 2,3 | 1 day |
| 6 | Measure site | 1 | 7 days |
| 7 | Mark out site | 5 | 5 days |
| 8 | Acquire stone | 2,4 | 3 days |
| 9 | Prepare site | 5,3 | 9 days |
| 10 | Build | 8,9 | 2 days |

- Display the Project Information

- View Project Timeline, Gant Chart, Network Diagram and capture the result of them.

## Exercise 3. Creating phases

Creating the following tasks

| ID | TASK NAME | PREDESCESSOR | DURATION |
| --- | --- | --- | --- |
| 1 | Pre-heat oven | - | 5 mins |
| 2 | Prepare meat | 1 | 5 mins |
| 3 | Prepare veg | 2 | 5 mins |
| 4 | Heat pan | 3 | 5 mins |
| 5 | Fry veg | 4 | 5 mins |

| 6 | Brown meat | 5 | 5 mins |
| --- | --- | --- | --- |
| 7 | Add stock and bring to a simmer | 6 | 5 mins |
| 8 | Cook in oven | 7 | 45 mins |

- Group the eight tasks so that the first task becomes a summary task (Make a casserole 1 day?) ∙ Display the Project Information

- View Project Timeline, Gant Chart, Network Diagram and capture the result of them.

## Exercise 4. Noah - Linking

Create the following links

| ID | TASK NAME | PREDESCESSOR | DURATION |
| --- | --- | --- | --- |
| 1 | Build boat | - | 7 days |
| 2 | Load supplies | 1 | 3 days |
| 3 | Load family | 1 | 6 days |
| 4 | Load animals | 1 | 7 days |
| 5 | Collect animals A-M | 1,4 | 12 days |
| 6 | Collect animals N-Z | 2,4 | 10 days |
| 7 | Float around | 5,6 | 7 days |

- Display the Project Information

- View Project Timeline, Gant Chart, Network Diagram and capture the result of them.

## Exercise 5. Pyramid - Multi level grouping

Create the following links

| ID | TASK NAME | PREDESCESSOR | DURATION |
| --- | --- | --- | --- |
| 1 | Build a pyramid | - | 1 day? |
| 2 | Acquire stone | 1 | 1 day? |
| 3 | Quarry stone | 2 | 3 wks |
| 4 | Transport stone | 3 | 5 days |
| 5 | Prepare stone | 4 | 3 wks |
| 6 | Prepare site | 5 | 1 day? |
| 7 | Dig foundations | 6 | 3 wks |
| 8 | Fill foundations | 7 | 2wks |
| 9 | Level ground | 8 | 1wk |
| 10 | Measure site | 9 | 7 days |
| 11 | Mark out site | 10 | 7 days |
| 12 | Build | 11 | 6 mons |

- Group the tasks as indicated above with 3 levels:

- Level 1 at task 1 includes task 2,6,12

- Level 2 at task 2 includes task 3,4,5, task 6 includes task 7,8,9,10,11

- Display the Project Information

- View Project Timeline, Gant Chart, Network Diagram and capture the result of them.

## Exercise 6. Creating a plan for Staff Training

| ID | TASK NAME | PREDESCESSOR | DURATION |
| --- | --- | --- | --- |
| 1 | Start with a skills gap analysis. | - | 7 days |
| 2 | Identify employees for career | 1 | 3 days |

ĐTTH Page 2 of 22 2021-2022

PROJECT MANAGEMENT IT - LAB IUH-SE

| 3 | Align with employee and company goals. | 2 | 6 days |
| --- | --- | --- | --- |
| 4 | Help them grow with you | 3 | 7 days |
| 5 | Use employee development plan | 4 | 1 days? |
| 6 | Consider an individual employee | 5 | 2 wks |
| 7 | A succession planning template | 6 | 1wks |
| 8 | Fit the learning opportunity to the training | 7 | 1 days? |
| 9 | Microlearning | 8 | 2 wks |
| 10 | On-the-job training | 9 | 5wks |
| 11 | Augmented reality | 10 | 1wks |
| 12 | Track results to inform your decisions | 11 | 7 days |

- Group the tasks as indicated above with 3 levels:

- Level 1 at task 1,2,3,4,5,8,12.

- Level 2 at task 5 includes task 6,7 and task 8 includes task 9,10,11

- Display the Project Information

- View Project Timeline, Gant Chart, Network Diagram and capture the result of them.

## Exercise 7. Recurring tasks

Create plan for a software project

| ID | TASK NAME | PREDESCESOR | DURATION |
| --- | --- | --- | --- |
| 1 | Planning | - | 1 wk |
| 2 | Requirement documents | 1 | 2 wks |
| 3 | Sign off | 2 | 1 day |
| 4 | Development | 3 | 10 wks |
| 5 | Testing | 4 | 4 wks |
| 6 | Implementation | 5 | 2 wks |
| 7 | Review | 6 | 1 wk |

- Add in a weekly meeting to run throughout the project with the following settings

- Name: Breakfast Meeting

- Duration: 1 hour

- Recurrence: Weekly

- Day: Monday

- Range: 08/01/2025 at 08:00 to end of the project.

- Calendar: Standard

- Display the Project Information

- View Project Timeline, Gantt Chart, Network Diagram and capture the result of them.

## Exercise 8. Travelling – task calendar

You intend to travel from HCM to Kuala Lumpur, Bangkok and then, come back to  HCM. Creating a plan for your trip.