# MODULE 4: ASSIGNING THE RESOURCE FOR A PROJECT

Capture the Project Information before and after assigning the resource

Họ tên : Nguyễn Thị Nga

MSSV : 21130791

## Exercise 1. Entering work resource

- Open the Exercise 1 (Module 3)

- Tab View => Resource Sheet

- Add the resource for this project bellow: Type Work (person)

| STT | Name | Initials | Groups | Max. Units | Std. Rate |
| --- | --- | --- | --- | --- | --- |
| 1. | David | Dav | Consultant | 100% | 8 |
| 2. | Brian | Bri | Staff | 200% | 7 |
| 3. | Mary | Mar | Staff | 100% | 7 |
| 4. | John | Joh | Staff | 100% | 7 |
| 5. | Worker 1: Liam | W1 | Worker | 300% | 6 |
| 6. | Worker 2: Chang | W2 | Worker | 200% | 6 |

- Assign the resource for each task

Tab Task => Gantt Chart => Select the task that you want to assign the resource

| ID | TASK NAME | RESOURCE |
| --- | --- | --- |
| 1 | clean machine | Worker 1, David |
| 2 | load raw materials | Worker 2 |
| 3 | prime machine | Mary |
| 4 | Test run | Brian |
| 5 | clean machine | Worker 1 |
| 6 | load raw materials | Worker 2 |
| 7 | prime machine | John |
| 8 | Test run | David |

## Exercise 2. Changing Working Time (Start Date 1/11/2024)\

- Open the Exercise 2 (Module 3)

- Tab View => Resource Sheet

- Add the resource for this project bellow: Type Material

| STT | Name | Type | Materials | Initials | Groups | Std. Rate |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | MDF | Material | Sheet | Md | Material | 20 |
| 2. | Flooring | Material | Pack | Fl | Material | 80 |
| 3. | Purple | Material | Roll | Pu | Material | 30 |
| 4. | Orange | Material | Roll | Or | Material | 120 |

- Assign the resource for each task

Tab Task => Gantt Chart => Select the task that you want to assign the resource

Select Tab Resource => Assign Resource

The information of resource that will assign for the task

| ID | TASK NAME | RESOURCE |
| --- | --- | --- |
| 1 | Visit estate agents | MDF [2] |
| 2 | View properties | Flooring [2] |
| 3 | Decide what to buy | Purple Material [1] |
| 4 | Make offer | Flooring [1], Purple Material [1] |
| 5 | Wait for decision | Flooring [1], Orange Material [1] |
| 6 | offer a accepted | Orange Material [2] |

## Exercise 3. Entering work resource

- Create the project bellowing:

| ID | TASK NAME | PREDECESSOR | DURATION |
| --- | --- | --- | --- |
| 1 | Planning | - | 1 wk |
| 2 | Requirement documents | 1 | 2 wks |
| 3 | Sign off | 2 | 1 day |
| 4 | Development | 3 | 10 wks |
| 5 | Testing | 4 | 4 wks |
| 6 | Implementation | 5 | 2 wks |
| 7 | Review | 6 | 1 wk |

- Add the resource for this project bellow: Type Work/Material

| STT | Name | Type | Materials | Initials | Groups | Std. Rate |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | PM | Work | Sponsor | PM | Staff | 10 |
| 2. | Designer | Work |  | Ds | Staff | 6 |
| 3. | Developer | Work |  | Dp | Staff | 8 |
| 4. | Tester | Work |  | Tt | Staff | 6 |
| 5. | Maintainer | Work |  | M | Staff | 5 |
| 6. | Operating System | Material | Unit | OS | Material | 120 |
| 7. | Internet Provider | Material | Unit | ISP | Material | 100 |
| 8. | Cable | Material | M | Cb | Material | 1 |
| 9. | Visual Studio | Material | Unit | VS | Material | 20 |

- Assign the resource for each task

| ID | TASK NAME | WORK | MATERIAL |
| --- | --- | --- | --- |
| 1 | Planning | PM |  |
| 2 | Requirement documents | PM, Designer |  |
| 3 | Sign off | PM |  |
| 4 | Development | Developer | Operating System [1], Visual Studio [1] |
| 5 | Testing | Tester |  |
| 6 | Implementation | Maintainer | Operating System, Visual Studio, Cable [100] |
| 7 | Review | PM, Maintainer |  |

## Exercise 4. Entering work resource

- Capture the Project Information before and after assigning the the source.

- Open the Exercise 3 (Module 3)

- Tab View => Resource Sheet => Resource Views

- Establish the resource that type is work (default) for the project below:

| STT | Name | Initials | Groups | Max. Units | Std. Rate |
| --- | --- | --- | --- | --- | --- |
| 1. | Architect | Arc | Consultant | 100% | 9 |
| 2. | Draftsperson | Dft | Staff | 200% | 7 |
| 3. | Building Clerk | BC | Staff | 100% | 8 |
| 4. | Supervisor | Sup | Staff | 100% | 12 |
| 5. | Rigger | Rig | Wages | 600% | 5 |
| 6. | Boilermaker | BM | Wages | 600% | 5 |
| 7. | Welder | Weld | Wages | 500% | 6 |
| 8. | Carpenter | Car | Wages | 800% | 7 |
| 9. | Painter | Ptr | Wages | 500% | 6 |
| 10. | Labourer | Lab | Wages | 1000% | 6 |
| 11. | Driver | Drv | Wages | 300% | 8 |
| 12. | No Barrier Fencing | NBF | Contractor | 100% | 3 |
| 13. | Rock Solid Concrete | RSC | Contractor | 100% | 4 |
| 14. | Listen Ear Audio | LEA | Contractor | 100% | 5 |
| 15. | In Focus Video | IFV | Contractor | 100% | 5 |
| 16. | Pure Grass Turf | PGT | Contractor | 100% | 5 |
| 17. | Building Inspector | BI | Government | 100% | 5 |
| 18. | High Jib Crane | HJC | Equipment | 100% | 7 |
| 19. | Grader | Grd | Equipment | 200% | 6 |
| 20. | Air Compressor | AC | Equipment | 100% | 7 |
| 21. | Utility Ute | Ute | Equipment | 200% | 5 |
| 22. | Electrician | Cap | Staff | 400% | 7 |
| 23. | Plumber | Plu | Staff | 400% | 5 |

- Establish the resource that type is material for the project below at the of Resource list above:

| STT | Name | Type | Materials | Initials | Groups | Std. Rate |
| --- | --- | --- | --- | --- | --- | --- |
| 24. | Astro Turf | Material | Square Metre | Grass | Material | 12 |
| 25. | Paint | Material | Ultre | Ute | Paint | 20 |

- Assign the resource for each task in the project

| ID | TASK NAME | RESOURCE |
| --- | --- | --- |
| 1 | Planning |  |
| 2 | Creating architectural plans | Architect, Draftsperson (200%), Building Clerk (25%) |
| 3 | Submit plans for approval | Architect |
| 4 | Order materials | Draftsperson, Building Clerk |
| 5 | Planning Completed |  |
| 6 | Site works |  |
| 7 | Erect fencing | No Barrier Fencing |
| 8 | Erect site building | Carpenter (400%), Supervisor, Laborer |
| 9 | Clear and level site | Supervisor, Grader (200%), Driver (200%) |
| 10 | Prepare drainage infrastructure | Supervisor (50%), Plumber (200%) |
| 11 | Prepare cabling infrastructure | Supervisor (50%), Electrician (300%) |
| 12 | Site works Completed |  |
| 13 | Building Construction |  |
| 14 | Pour foundations | Rock Solid Concrete |
| 15 | Erect steelwork | Supervisor (50%), Rigger (600%), Boilermaker (600%), Welder (500%), Laborer (600%), Driver (200%), High Jib Crane, Utility |
| 16 | Erect wall | Supervisor [50%], Carpenter [700%], Laborer [400%], Driver, Grader, Air Compressor, Electrician [75%], Plumber [25%] |
| 17 | Install roofing superstructure | Supervisor [50%], Rigger [500%], Boilermaker [500%], Welder [300%], Laborer [500%], Driver [200%], High Jib Crane, Utility, Air Compressor, Plumber [50%] |
| 18 | Install roofing retracting mechanism | Supervisor [50%], Welder, Boilermaker [200%], Rigger [200%], Electrician [200%], Driver, High Jib Crane |
| 19 | Erect seating tiers | Supervisor [50%], Carpenter [800%], Welder [200%], Boilermaker [200%], Laborer [500%], Driver, Utility, Air Compressor |
| 20 | Building Construction Completed |  |
| 21 | Fit Out |  |
| 22 | Fit all windows and doors | Carpenter [500%], Laborer [200%] |
| 23 | Install electrical cabling | Electrician [300%], Laborer [200%] |
| 24 | Install electrical fittings and fixtures | Electrician [300%] |
| 25 | Install all plumbing | Plumber [200%], Laborer [200%] |
| 26 | Install plumbing fixtures and fittings | Plumber [200%] |
| 27 | Lay astro turf | Pure Grass Turf |
| 28 | Erect handrails and fencing | Welder [400%], Boilermaker [200%] |
| 29 | Paint rooms, fixtures, fittings, etc. | Painter [500%] |
| 30 | Install PA system | Listen Ear Audio |
| 31 | Install video imaging equipment | In Focus Video |
| 32 | Fit out control room | Electrician [200%], Listen Ear Audio, In Focus Video |
| 33 | Fit out Completed |  |
| 34 | Commissioning |  |
| 35 | Test roof mechanism | Supervisor, Electrician [200%], Rigger |
| 36 | Test PA system | Listen Ear Audio |
| 37 | Test video imaging equipment | In Focus Video |
| 38 | Test control room equipment | Supervisor, Listen Ear Audio [20%], In Focus Video [20%], Architect, Electrician [200%] |
| 39 | Obtain official occupancy | Architect, Building Clerk, Supervisor |
| 40 | Obtain safety certification | Supervisor |
| 41 | Official opening | Supervisor [200%] |
| 42 | Commissioning Completed |  |

## Exercise 5

Creating the following tasks (Project Start Date 6/12/2024)

Establish working time: MSSV_Time

1. Working time: Mon – Fri: 8AM – 11AM, Sat: 11AM-9PM

2. Nonworking time: Sun

3. Exception: Nonworking time: 24/12/2024, 1/1/2022

| STT | Name | Duration | Dependencies |
| --- | --- | --- | --- |
| 1 | The Engagement | 1 day |  |
| 2 | The Venue - Confirm Dates | 4 wks | 1 |
| 3 | The Photographer | 3 wks | 2 |
| 4 | The Cars | 4 wks | 2 |
| 5 | The DJ | 1 wk | 2 |
| 6 | The Dress - Find the Perfect Dress | 3 wks | 2 |
| 7 | The Venue - Confirm Menu | 4 wks | 2 |
| 8 | The Venue - Pay Deposit | 2 hrs | 7 |
| 9 | The Dress - Pay for Dress | 1 hr | 6 |
| 10 | Invitations - Confirm Design | 2 wks | 6 |
| 11 | The Flowers | 2 wks | 6 |
| 12 | Invitations - Confirm Numbers | 1 wk | 10 |
| 13 | Inviations - Invites Produced | 2 mons | 12 |
| 14 | Review progress | 4 wks | 3,4,5,8,9,11,12,13 |
| 15 | Invitations - Send Out | 1 wk | 13 |
| 16 | The Dress - First Fitting | 2 hrs | 9 |
| 17 | Invitations - Review RSVP's | 1 wk | 15 |
| 18 | The Venue - Confirm Numbers | 2 hrs | 17 |
| 19 | The Venue - Confirm Timings | 2 hrs | 18 |
| 20 | The Venue - Pay Balance | 1 hr | 19 |
| 21 | The Dress- Final Fitting | 2hr | 20 |

- Create a milestone task at the end: The Big day (P) (Dependencies: 19,21)

- Creating the summary tasks :

- Before 6 month to go (Task 2,3,4,5,6,7)

- 6 month to go (Task 8,9,10,11)

- 5 month to go (Task 12,13)

- 4 month to go (Task 14)

- 3 month to go (Task 15)

- 2 month to go (Task 16,17)

- 1 month to go (Task 18,19,20,21)

- Establish the resource table:

| STT | Name | Type | Initials | Groups | Max. Units | Std. Rate |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Venue Material | Material | V | None | None | £3,000.00 |
| 2 | Photgraphs | Material | V | None | None | £1,000.00 |
| 3 | Flowers | Material | P | None | None | £900.00 |
| 4 | Cars | Material | F | None | None | £500.00 |
| 5 | DJ | Material | C | None | None | £250.00 |
| 6 | Guest | Work | D | None | 8000% | £25/1hr |

- Assign the resource for each task in the project

| STT | Name | Resource |
| --- | --- | --- |
| 1 |  |  |
| 2 | The Engagement |  |
| 3 | The Venue - Confirm Dates | Venue[1] |
| 4 | The Photographer | Photgraphs[1] |
| 5 | The Cars | Cars[1] |
| 6 | The DJ | DJ[1] |
| 7 | The Dress - Find the Perfect Dress |  |
| 8 | The Venue - Confirm Menu |  |
| 9 | The Venue - Pay Deposit |  |
| 10 | The Dress - Pay for Dress |  |
| 11 | Invitations - Confirm Design |  |
| 12 | The Flowers | Flowers[1] |
| 13 | Invitations - Confirm Numbers |  |
| 14 | Inviations - Invites Produced |  |
| 15 | Review progress |  |
| 16 | Invitations - Send Out |  |
| 17 | The Dress - First Fitting |  |
| 18 | Invitations - Review RSVP's |  |
| 19 | The Venue - Confirm Numbers |  |
| 20 | The Venue - Confirm Timings |  |
| 21 | The Venue - Pay Balance | Guests[7,000%] |
| 22 | The Dress- Final Fitting |  |